# Graduate onboarding programme 2027 – planning meeting

Present: Elena Rossi, Samuel Okoye, Mei Lin

Elena reported that only 12 of 25 mentors have signed up so far. This is a problem now because mentor matching starts next week.

The laptops for the new graduates must arrive from procurement before the start date of 2027-01-11.

Samuel noted that if the city office renovation runs late, the induction week may need another venue.

The team assumes all graduates will pass their background checks before the start date.

The group decided to run the first week fully in person.

Mei will draft the welcome pack by 2026-11-13.

Elena will send a reminder to the managers who have not signed up as mentors.